## Slide 1: Capital Outlay: Review and Funding Processes
Michael D. Maul, Associate Director
June 2019 Department of Planning and Budget

## Slide 2
Training Objectives:
- Awareness of Present Capital Environment - Understanding of DPB Procedures on Capital

## Slide 3: Capital Definition
Operating Budget (Non-Capital):
Routine operating and maintenance costs for property, plans, and equipment (regardless of expense or financing method)
Optional when under designated thresholds of above categories
Definition of Capital:
Acquisition (All types)
Improvements ($3.0 million)
Construction ($3.0 million or ≥5,000 sq. ft.)

## Slide 4
Evolution of Capital Outlay Funding Environment: past to present
Capital Budget Development: step-by-step
Capital Pool Process: step-by-step
Equipment Funding: when to request
Non-pool Projects: purpose and types
Maintenance Reserve: eligibility criteria; M-R FIX
Capital Leases: purpose and types
Emergency Projects: eligibility criteria
ESCO Projects: appropriate cases
Environmental Impact Reports: new checkbox on CO-2
Capital Items we will cover today

## Slide 5: Present Capital Situation
Capital Environment
Debt capacity limited
Unlikely to have large bond package
Evolution of the pool process
Background of Chapter 1, 2008 Special Session 1 (Pool Process)
Relationship of DPB and DGS Division of Engineering & Buildings (DEB)
Role of the Six Pack Committee

## Slide 6: Phases in Capital Budget Development
June - August
DEB works on cost review and DPB analysts verify programmatic need
DEB finishes cost review
Governor decides which projects to include in the budget bill and the six year capital outlay plan
LEGISLATURE ACTS
August - Early September
GOVERNOR ACTS
DPB issues instructions to agencies
Agencies generate & submit requests
DPB Analyst Review
Identifies projects for DEB cost review
Six Pack meets to recommend capital projects for the 6 year capital outlay plan, using analyses from SCHEV, DPB, Money Committees Staff and DEB
AD’s and Budget Director provide, and SOF and Governor’s staff approve, capital recommendations for the Governor’s consideration
General Assembly takes action on the Governor's proposal
BUDGET PREPARATION
REVIEW & RECOMMENDATION
DPB analysts make recommendations to Associate Directors (AD)
Mid September - November
December – March or April (longer GA session)
Notes: AGENCY BUDGET PREPARATION
DPB provides guidance on Governor's priorities and instructions for preparing budget requests (Budget Instructions)
Agencies analyze programs and needs as they prepare requests
Agencies submit budget requests to DPB
BUDGET REVIEW & RECOMMENDATION
DPB analyzes budget requests to verify costs, confirm need for services, investigate funding alternatives, identify policy issues, and review performance
DPB, working with the Governor and Governor's Secretaries, prepares proposed budget to reflect Governor's priorities
Governor makes final decisions regarding what to include in the budget
Governor submits budget to General Assembly

## Slide 7: Budget Development: step-by-step

## Slide 8: Capital Budget Request Types:
Funding supplements for existing capital projects;
Funding equipment for previously funded projects;
Proceed further on projects authorized for preplanning or detailed planning stages only;
New capital projects (improvements, major repairs, renovations, new construction, acquisitions, etc.); and
Authorize new capital leases or renew existing leases.

## Slide 9: Priorities
Immediate safety/health/regulatory/environmental concerns;
Equipment for projects previously approved for construction;
Supplemental funding for projects previously approved for construction;
Directly support one of the Governor’s priorities;
Previously authorized for preplanning or detailed planning expected to be reviewed by DEB by November, 2019;
Take advantage of one-time economic opportunities; or
Address significant maintenance reserve-type issues at existing facilities.

## Slide 10: Capital Budget Requests:
Capital Budget Request (CBR) in PB System
Project description/justification
Scope
Estimated $$ cost
DGS Project Planner Form CR-1: help develop scope and project costs

## Slide 11: Capital pool process: step-by-step

## Slide 12
Funding source
Funding criteria
Central Planning Fund
Agencies’ own nongeneral funds
State general fund support
DEB reviews both preplanning and detailed planning
DEB estimate for total project cost is based on detailed planning
Planning funding for projects under pool process
Preplanning (up to $250,000)
Detailed Planning (4% new construction; 5% renovation)

## Slide 13: Construction Cost Review under Pool Process
Funding for projects put into a pool of authorized funding
Projects are not guaranteed any specific $$ amount from the pool
If detailed planning has not yet been done, DEB reviews and provides initial cost targets
After detailed planning is reviewed by DEB, it issues a Funding Report and the agency submits a CO-2 equal to the amount authorized in the funding report
CO-2 approved by DEB; sent to DPB; DPB reviews in conjunction with a BEX transferring funding from the pool to the agency for the capital project
Bid $ > $Funding Report
Reduce the scope, or
Use own nongeneral funds, or
Request additional funding from the General Assembly
Appeal to DEB/DPB for additional funding amount up to 5 %
Submit revised CO-2
DPB only allot funding = to the bid
$Bid > $Funding Report + 5 %
$Bid ≠ $ Funding Report
Scenarios
Bid $ < $ Funding Report

## Slide 14
Umbrella Pool Projects vs Phased Pool Projects
Umbrella projects funding:
Amount of funding available is up to the budgeted funding amount (i.e., umbrella projects not eligible for the 5% cost overrun)
Phased projects funding:
5% cost overrun rule is applicable
Any funding unspent from a completed project will be transferred back to the pool

## Slide 15: The Pool Process Phases, Critical Milestones and Detailed Cost Reviews
1
2
Detailed cost review ensures the project is “right-sized” and the funding is appropriate to complete the design and construct the facility. This establishes the basis for the application of the “105% rule.” This is the most critical “GO” for an agency in the pool process as it typically allows them to “proceed with execution.”
Cost check ensures bids are within authorized funding; based upon bid prices, either maintain current project funding (typically the case), reduce project funding if exceptionally low bids received, or increase project funding via an agency appeal up to 105% of that amount determined at milestone 1. If bids result in project(pool $) > 105% as defined at milestone 1, then agency must either reduce scope, provide more agency funding, or request additional $ from GA.
.
CONSTRUCTION
DESIGN
Schematic Cost Review
(Schematic Report)
(Guidance/Dialogue with Agencies)
WORKING DRAWINGS
Design 3
PRELIMINARY
Design 2
SCHEMATIC
Design 1
Preplanning
Detailed Planning
Capital Budget Request
Cost Review (CO-2)
Post- Bid Receipt Cost Check(CO-2/8); Building Permit (CO-17)
2
Preliminary Cost Review (CO-2)
1
Warranty & close-out
(~ 1 year)
Construction
Project
Phases
Funding
Phases
Certificate of Occupancy (CO-13.3)
Project Completion Report (CO-14)

## Slide 16: Equipment funding: when to request

## Slide 17: Equipment Funding
Issue
Some capital construction pools include equipment funding (FF&E) for each project, while most pools do not
Each agency should talk to their DPB analyst to determine whether a construction pool includes equipment or not
Most times the pool will not include FF&E and the agency will need to submit a separate capital budget request to DPB for this funding
POOL | FF&E
2013 Chapter 806 | Excluded
2014 Chapter 1 Caboose | Excluded
2014 Chapter 2 | Included
2015 Chapter 665 | Excluded
2016 Chapter 759/769 | Excluded
2017 Chapter 836 | Excluded
2018 Chapter 2 | Excluded
2019 Chapter 854 | Excluded

## Slide 18: Equipment Cont’d
Process
DPB will NOT initiate a request for equipment funding – it is the responsibility of the agency to submit a request
Agencies need to judge the timing of the request for equipment in accordance with the anticipated completion date for the project (this is also true for stand alone projects that require FF&E)
DPB will not recommend funding equipment unless it needs to become available within 6-9 months of project completion
DPB will base its funding recommendation on the amount identified in the DEB funding report; if agency request exceeds that amount, it must provide justification

## Slide 19: Other Projects: Non-pool Maintenance Reserve Capital leases Emergencies ESCOs

## Slide 20: Non-pool capital projects
Projects not subject to pool process include:
Traditional NGF Projects
DGIF, DMV, VDOT, higher education auxiliary, federal
Revenue Bond Projects
Revenue bond projects 9(c) and 9(d)
Other GF and bond projects
Authorized as stand alone projects in Appropriation Act
Mostly higher ed
Up to 20% will be allotted for A&E (architectural and engineering services), with balance allotted after construction contract awarded

## Slide 21: Maintenance Reserve
Process
Agencies free to use funds on projects, as needed, consistent with the guidelines for maintenance reserve use
Agencies report annually on previous fiscal year’s expenditures
If agencies fail to follow criteria, subject to having projects reviewed in advance and validated

## Slide 22: Maintenance Reserve Funding Calculations
DGS COVA Trax/M-R FIX Web Portal
Data to be used to allocate maintenance reserve funding, per requirements of § 4-9.04 d. of the 2019 Appropriation Act:
The Department of Planning and Budget shall revise the formula used to make allocation recommendations for the state’s maintenance reserve funding to account for higher maintenance needs resulting from poor facility condition, aging of facilities, and differences in facility use.
M-R FIX data will be used to help determine the distribution of maintenance reserve funding provided to each agency and institution beginning with the upcoming 2020 – 2022 biennium
Agencies need to incorporate data into M-R FIX by August 30, 2019
In addition, agencies are being asked to add data associated with EO 24, identifying state facilities vulnerable to extreme weather

## Slide 23: Capital Leases
Subject to capital outlay process since leases can affect debt capacity
Criteria of Capital Lease
  Building ownership reverts to agency at end of lease at no or nominal cost
  Lease for long duration that covers a substantial portion of the useful life of the property
Lease vs purchase analysis
  What’s most effective and economical: long term lease or a new building
  Do analysis at least a year or two before current lease ends
  Work with DGS to proceed with capital lease or buying existing building
Lease payments paid from operating funds

## Slide 24: Projects Not Included in the Budget
Basic assumption of Appropriation Act that the General Assembly must approve capital projects; however, “emergencies” or “opportunities” do not happen on schedule.
When Immediate Need arises between GA sessions for a capital project
  Governor granted authority to create capital project in certain situations:
    Emergency situations
    Higher ed project to be funded by revenues or sponsored programs or private gifts and indirect cost recoveries
    Plant or property received as a gift
    Project recommended by Tobacco Indemnification and Community Revitalization Commission or Virginia Tobacco Settlement Foundation
Criteria
  Nongeneral funds sources available for both capital and operating elements of project
  Governor feels the project results in measurable benefit for the state or cost avoidance
  Detailed justification for project includes cost estimates and fund sources
Process
  Agency notifies DPB of emergency or immediate need
  DPB prepares decision brief for the Governor
  Governor either authorizes or declines to authorize the project
  Authorized project still subject to DEB requirements, including capital outlay form submissions

## Slide 25: ESCO Projects
Key features of the Energy Service Company (ESCO) projects:
  Results in significant energy savings
  DMME must review and approve
  DGS has a standard contract and list of approved vendors
  Maintenance reserve funding can be used on activity or component that results in energy savings that equal project costs
  Levels of Approval
  Operating Expense when:
    Total cost ≤ $3million, or ≥$ 3million but ≤ $7 million if energy savings offset the cost
  Capital Expense when:
    Total cost ≥ $3 million but ≤ $7 million and energy savings do NOT offset the cost
    Total cost greater than $7 million
  DPB notification required for any project costing ≥ $ 250,000

## Slide 26: Environmental Impact Reports
Construction projects costing more than $500,000 required to provide an environmental impact report (EIR) to DEQ (§ 10.1-1188, Code of Virginia)
The EIR is reviewed by state natural/historic resources agencies and approved by the Secretary of Administration
Department of Accounts (DOA) is not supposed to release funds for capital projects until the EIR is approved (§ 10.1-1190, Code of Virginia)
DPB is working with DGS to include a check box on CO-2 forms for agencies to fill out related to EIR’s to help provide guidance to DOA
Agencies will be notified once these efforts are in place

## Slide 27: Any Questions?

## Slide 28
Department of Planning and Budget
Michael D. Maul Associate Director (804) 786-6657 Michael.Maul@dpb.virginia.gov | Emily Grimes Capital Coordinator (804) 786-1687 Emily.Grimes@dpb.virginia.gov
Additional Information can be found at:
Virginia Department of Planning and Budget
dpb.virginia.gov
Call or email your DPB budget analyst with questions for best results